| SUMMARY TASK (LEVEL 1) | SUBTASK (SUB-LEVEL) | TASK DESCRIPTION | START DATE | STOP DATE | EXPECTED OUTCOMES | PERSON(S) RESPONSIBLE | OSHR ASSISTANCE NEEDED/RESPONSIBLE PARTY |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Communication Plan Development |  |  | Communication plan is developed to educate affected employees of CB | Project Team |  |
|  | 1.1 | Identify Employees Included in the Project |  |  |  | CBC/Project Team |  |
| 2 |  | Accept, Add and/or Revise Competencies |  |  | Establish validated competencies |  |  |
|  | 2.1 | Identify Focus Group Participants |  |  | Employees with similar work are formed into Focus Group/s | CBC/HR Classification Analyst/Project Leader/ Managers and Supervisors |  |
|  | 2.2 | Conduct Focus Groups for competency validation, revisions or additions |  |  | Employee Input Considered | CBC/HR Classification Analyst/Project Leader |  |
|  | 2.3 | Additions, major revisions reviewed by OSHR HR Partner |  |  | Competencies Approved | CBC/HR Classification Analyst/OSHR HR Partner |  |
| 3 |  | Accept/Adapt Market Rates |  |  | Review and use the Statewide Market Rates established for new banded classes or establish market reference rates | CBC/HR Classification Analyst/ Compensation Specialist |  |
|  | 3.1 | Develop Market Reference Rates |  |  | If required, establish Market Reference Rates following methodology introduced in Compensation Manual and submit to assigned HR Partner | CBC/HR Classification Analyst/ Compensation Specialist |  |
|  | 3.1.1 | Determine if market reference rates are needed |  |  |  | CBC/Project Leader/Project Team |  |
|  | 3.1.2 | Identify relevant labor market |  |  |  | CBC/Project Leader/Project Team |  |
|  | 3.1.3 | Determine if data is available in OSHR Compensation Library |  |  |  | CBC/Project Leader/Project Team |  |
|  | 3.1.4 | Identify survey participants |  |  |  | CBC/Project Leader/Project Team |  |
|  | 3.1.5 | Gather Compensation Information |  |  |  | CBC/Project Leader/Project Team |  |
|  | 3.1.6 | Analyze Compensation Information & recommend market reference rates |  |  |  | CBC/Project Leader/Project Team |  |
|  | 3.1.7 | Submit market reference rates for approval |  |  |  | CBC/Project Leader/Project Team |  |
| 4 |  | Allocate positions to banded classes |  |  | Initial allocation list of positions is developed. List provides partial information. Complete information finalized prior to competency evaluations by managers. | CBC/Agency HR Classification Analyst and Managers. Requires approval by OSHR HR Partner. |  |
|  | 4.1 | HR prepares initial list |  |  |  |  |  |
|  | 4.2 | Reviewed by Management |  |  |  |  |  |
|  | 4.3 | Sent to OSHR for Review |  |  |  |  |  |
| 5 |  | Employee & Manager Training Presented |  |  | Orientation/Training given to employees and managers of specifically affected occupational group |  |  |
|  | 5.1 | Adapt OSHR training materials based on Agency changes and train managers on competency evaluation salary determination, and career development plans |  |  | Managers learn to perform competency evaluations and determine employee ratings of Contributing, Journey, or Advanced | CBC/HR Classification Analyst |  |
|  | 5.2 | Adapt OSHR training materials based on Agency changes and orient employees |  |  | Employees receive orientation to new classes, competencies, pay guidelines, timelines and the system in general | CBC/HR Classification Analyst |  |
|  | 5.3 | Adapt OSHR training materials for managers on others system aspects |  |  | Train managers in posting, recruitment, selection, behavioral interviewing, etc. | CBC/HR Classification Analyst |  |
| 6 |  | Initial Competency Evaluations/ Career Planning/ Determining Pay |  |  | Managers perform initial competency evaluations, document career development plans, and determine pay | Managers and Supervisors/ HR Classification Analyst and Compensation Specialist set and review Pay |  |
|  | 6.1 | Agency HR reviews and consults with management as needed |  |  | Consistent application of pay factors assured | Managers and Supervisors/ HR Classification Analyst and Compensation Specialist set and review Pay |  |
| 7 |  | Final Allocation list |  |  | Prepare final allocation list and discusses with OSHR any instances of difficulty in classification | HR Classification Analyst submits final allocation list to OSHR HR Partner for review and approval |  |
|  | 7.1 | Manager Prepares |  |  |  |  |  |
|  | 7.2 | HR Reviews |  |  |  |  |  |
|  | 7.3 | Submit to OSHR for approval |  |  |  |  |  |
|  | 7.4 | Updates to PMIS |  |  | Positions moved to new classification titles After allocation list approved by OSHR | Agency Salary Administration Specialist |  |
| 8 |  | Project Report |  |  | Summarizes the specifics of the project. Submitted to OSHR HR Partner after allocation list is finalized | CBC/HR Classification Analyst/Project Leader |  |